## conic_sections
Phase | Milestone | Status | Details | Target
Completed (v0.1.0 → v0.2.0)
1 | Project scaffolding & CI/CD | Done ✓ | pyproject.toml, src layout, GitHub Actions (3.11/3.12/3.13), pre-commit, ruff+mypy strict | v0.1.0
2 | Core camera model | Done ✓ | Pinhole + fish-eye camera, 21 unit tests, 99% coverage on core/ | v0.1.0
3 | ModernGL proof-of-concept | Done ✓ | GLFW window, Blinn-Phong shaders, orbit camera, procedural cube, ChArUco texture, ground-plane grid | v0.2.0
Next Steps
4 | Camera model migration | Next → | Port ray-tracing math to GPU shaders; project camera intrinsics into the render pipeline | v0.3.0
5 | Blender asset pipeline | Planned | glTF 2.0 (.glb/.gltf) loader via trimesh/pygltflib; materials & textures; OBJ fallback | v0.4.0
6 | Multi-camera system | Planned | Configurable camera rigs; split-screen or switchable viewports; extrinsic calibration | v0.5.0
7 | Virtual environment navigation | Planned | Drone/vehicle controls; keyboard+mouse or gamepad input; collision detection | v0.6.0
8 | VR environment support | Future | OpenXR integration; stereoscopic rendering; head tracking | v1.0.0

## hopf_fibration
Phase | Milestone | Status | Details | Target
Completed (v0.1.0)
1 | Project scaffolding & sphere renderer | Done ✓ | UV sphere with Blinn-Phong + alpha transparency, orbit camera, ground-plane grid, 27 tests, CI/CD | v0.1.0
Next Steps
2 | Path generation on S² | Next → | Great circles, loxodromes, arbitrary parametric curves on the sphere; line shaders for path rendering | v0.2.0
3 | Parallel transport animation | Planned | Animate tangent frame along paths; Levi-Civita connection; visualise holonomy angle | v0.3.0
4 | Hopf fibration visualisation | Planned | Map S³ → S² fibres; render circles in R³ via stereographic projection from S³; fibre colouring | v0.4.0
5 | Interactive controls | Planned | Path selection (click on sphere), fibre density slider, animation speed, Berry phase readout | v0.5.0
6 | Educational overlays | Future | Annotated diagrams, formula display, step-by-step walkthrough mode | v1.0.0

## parallel_transport
Phase | Milestone | Status | Details | Target
Completed (v0.1.0)
1 | Project scaffolding & core math | Done ✓ | src layout, hatchling, CI/CD, pre-commit, ruff+mypy strict, quaternion algebra module, sphere geometry module, 38 tests, 99% coverage | v0.1.0
Next Steps
2 | Physics module | Next → | Port Hamiltonian, parallel transport, S1 bundle phases, Stokes' theorem, Gauss-Bonnet from qt_sphere/quaternions.py | v0.2.0
3 | PyQt5 UI port | Planned | Port MainWindow + matplotlib subplots from qt_sphere; sphere subplot, stereo subplot, settings.yaml loader | v0.3.0
4 | Additional subplots | Planned | Quaternion tuner (drag interaction), S1 phase plots (global/geometric/dynamic), stereographic projection overlay | v0.4.0
5 | ModernGL migration | Planned | Replace matplotlib 3D sphere with GPU-accelerated renderer (match conic_sections/hopf_fibration stack) | v0.5.0
6 | Interactive controls & overlays | Future | Path selection, animation controls, vector field overlays, Berry phase readout | v1.0.0

## Study Plan — Arm Interview
# | Topic | Type | Task | Done? | Resources
Git & Version Control
1 | Git fundamentals | Reading | Review branching, merging, rebasing, cherry-pick, interactive rebase; practice on a toy repo |  | Pro Git Book — Branching & Merging: https://git-scm.com/book/en/v2/Git-Branching-Basic-Branching-and-Merging Atlassian — Git Rebase Tutorial: https://www.atlassian.com/git/tutorials/rewriting-history/git-rebase
2 | Git workflows | Reading | Understand Gitflow vs trunk-based development; document which you use and why |  | Atlassian — Gitflow Workflow: https://www.atlassian.com/git/tutorials/comparing-workflows/gitflow-workflow Trunk-Based Development: https://trunkbaseddevelopment.com/
3 | Pre-commit hooks | Exercise | Add a new custom hook to one of your repos (e.g., check CHANGELOG updated) |  | pre-commit Documentation: https://pre-commit.com/ pre-commit Hooks Gallery: https://pre-commit.com/hooks.html
4 | CI/CD pipelines | Exercise | Walk through your GitHub Actions YAML; be ready to explain every step in an interview |  | GitHub Actions Documentation: https://docs.github.com/en/actions GitHub Actions — Workflow Syntax: https://docs.github.com/en/actions/using-workflows/workflow-syntax-for-github-actions
ModernGL & GPU Rendering Pipeline
5 | OpenGL pipeline stages | Reading | Study vertex → tessellation → geometry → rasterisation → fragment pipeline; draw a diagram |  | Learn OpenGL — Rendering Pipeline: https://learnopengl.com/Getting-started/Hello-Triangle Khronos OpenGL Wiki — Pipeline: https://www.khronos.org/opengl/wiki/Rendering_Pipeline_Overview
6 | Shader programming | Exercise | Write a custom vertex+fragment shader pair beyond Blinn-Phong (e.g., toon shading, normal mapping) |  | Learn OpenGL — Shaders: https://learnopengl.com/Getting-started/Shaders ModernGL Documentation: https://moderngl.readthedocs.io/en/stable/ The Book of Shaders: https://thebookofshaders.com/
7 | Coordinate systems | Reading | Model → World → View → Clip → NDC → Screen; understand row-major vs column-major conventions |  | Learn OpenGL — Coordinate Systems: https://learnopengl.com/Getting-started/Coordinate-Systems Learn OpenGL — Transformations: https://learnopengl.com/Getting-started/Transformations
8 | Uniform buffers & VAOs | Exercise | Refactor conic_sections renderer to use UBOs for camera matrices; explain the performance benefit |  | Learn OpenGL — Advanced GLSL (UBOs): https://learnopengl.com/Advanced-OpenGL/Advanced-GLSL Khronos — Uniform Buffer Objects: https://www.khronos.org/opengl/wiki/Uniform_Buffer_Object
9 | Depth testing & blending | Reading | Understand z-buffer, depth precision issues, order-independent transparency approaches |  | Learn OpenGL — Depth Testing: https://learnopengl.com/Advanced-OpenGL/Depth-testing Learn OpenGL — Blending: https://learnopengl.com/Advanced-OpenGL/Blending
GPU Architecture (Arm Mali Focus)
10 | Arm Mali architecture overview | Reading | Study tile-based deferred rendering (TBDR); understand how Mali differs from immediate-mode GPUs (NVIDIA/AMD) |  | Arm — Mali GPU Architecture (TBDR): https://developer.arm.com/documentation/102662/latest/ Arm — GPU Best Practices Guide: https://developer.arm.com/documentation/101897/latest/
11 | Mali GPU generations | Reading | Review Mali-G series (G78, G710, G720, G925); understand Valhall and 5th-gen architecture |  | Arm — Mali GPU Product Pages: https://developer.arm.com/Processors/Mali-G720 Arm — 5th Gen GPU Architecture Blog: https://community.arm.com/arm-community-blogs/b/graphics-gaming-and-vr-blog
12 | GPU compute & ML | Reading | Study how Mali handles ML workloads; Arm NN SDK, NNAPI, NPU vs GPU compute trade-offs |  | Arm NN SDK Documentation: https://developer.arm.com/documentation/102049/latest/ Arm — ML on Arm Processors: https://developer.arm.com/solutions/machine-learning-on-arm
13 | Shader core architecture | Reading | Execution engine, warp/wavefront scheduling, register file, texture units, tile memory |  | Arm — Valhall Shader Core: https://developer.arm.com/documentation/102203/latest/ Arm — Understanding GPU Shader Cores: https://developer.arm.com/documentation/102662/latest/
14 | Performance optimisation | Exercise | Profile one of your ModernGL apps; identify bottlenecks (CPU-bound vs GPU-bound vs bandwidth) |  | Arm — Streamline Performance Analyzer: https://developer.arm.com/Tools%20and%20Software/Streamline%20Performance%20Analyzer Arm — Mali Offline Compiler: https://developer.arm.com/Tools%20and%20Software/Mali%20Offline%20Compiler
Industry-Standard Software Development
15 | Testing strategy | Reading | Unit vs integration vs system tests; test pyramid; fixture patterns; mocking strategies |  | Martin Fowler — Test Pyramid: https://martinfowler.com/articles/practical-test-pyramid.html pytest Documentation: https://docs.pytest.org/en/stable/
16 | Code review practices | Reading | Review Google's code review guidelines; prepare to discuss your PR review approach |  | Google — Code Review Best Practices: https://google.github.io/eng-practices/review/ Google — How to Write Good CLs: https://google.github.io/eng-practices/review/developer/
17 | Design patterns | Reading | Focus on patterns relevant to GPU/graphics: Command, Observer, Strategy, Factory, Builder |  | Refactoring Guru — Design Patterns: https://refactoring.guru/design-patterns Game Programming Patterns (free): https://gameprogrammingpatterns.com/contents.html
18 | API design | Exercise | Review your public API surfaces (quaternion.py, sphere.py); document design decisions and trade-offs |  | Google — API Design Guide: https://cloud.google.com/apis/design Python — API Design Tips: https://docs.python-guide.org/writing/structure/
19 | Technical documentation | Exercise | Write a short architecture decision record (ADR) for one key decision in your projects |  | ADR GitHub — Architecture Decision Records: https://adr.github.io/ Documenting Architecture Decisions (Nygard): https://cognitect.com/blog/2011/11/15/documenting-architecture-decisions
20 | Debugging & profiling | Exercise | Use cProfile/py-spy on your Python code; learn to read flame graphs; document findings |  | Python — cProfile Documentation: https://docs.python.org/3/library/profile.html py-spy — Sampling Profiler: https://github.com/benfred/py-spy Brendan Gregg — Flame Graphs: https://www.brendangregg.com/flamegraphs.html
Portfolio Presentation
21 | README quality | Exercise | Ensure all three repos have clear READMEs with screenshots/GIFs, install instructions, architecture overview |  | Make a README — Guide: https://www.makeareadme.com/ Awesome README Examples: https://github.com/matiassingers/awesome-readme
22 | Demo preparation | Exercise | Record a 2-minute screen recording of each app running; prepare talking points for each |  | OBS Studio (screen recording): https://obsproject.com/ asciinema (terminal recording): https://asciinema.org/
23 | Code walkthrough prep | Exercise | Pick 2-3 interesting code sections to walk through in interview (quaternion algebra, shader pipeline, camera model) |  | Staff Engineer — Technical Interview Prep: https://staffeng.com/guides/ Coding Interview University: https://github.com/jwasham/coding-interview-university
24 | STAR stories | Exercise | Prepare 3-4 STAR format stories: challenging bug, architecture decision, performance win, collaboration |  | STAR Method — Interview Guide: https://www.themuse.com/advice/star-interview-method Amazon Leadership Principles & STAR: https://www.aboutamazon.com/about-us/leadership-principles